## Slide 1: LCME Self-Study Task Force
September 2023

## Slide 2: LCME Accreditation Process
8 year cycle
Begins with a year long self-study process which comprises the completion of a Data Collection Instrument (DCI) and Independent Student Analysis (ISA) which along with a self-study summary report are sent to the LCME 3 months prior to a 2 ½ day site visit (February 2-5, 2025)
Last site visit in February 2017 the LCME found five of the 93 elements to be satisfactory with monitoring and 11 elements unsatisfactory
Status reports were submitted to the LCME yearly on elements that were satisfactory with monitoring and unsatisfactory
As of March 2023, one element is still satisfactory with monitoring (oversight of extramural electives) and two are unsatisfactory (research opportunities and career advising)

## Slide 3: Self-study Process
Self-study Task Force is responsible for preparing the final self-study summary report coordinated by Faculty Accreditation Lead (FAL) based on the information submitted in the DCI and ISA.
Task Force should represent the broad constituencies of the SOM and include representatives from the following groups: SOM administrators, department chairs, junior/senior faculty, medical students, alumni in local residency programs, and clinical affiliates.
A Self-study Steering committee was formed in May to oversee the work of the self-study committees and insure the process stays on track. Members include: M. Foertsch, A. Gandy, C. Nichols, D. Payne, D. Ray, R. Riley, J. Thornhill, and E. Williams and represent keys areas of administration, medical education, and student services.

## Slide 4: Self-Study Task Force Charge/Report
The Self-Study Task Force is responsible for conducting the self-study, supported by the FAL. Using their knowledge of the intent of the LCME accreditation elements, task force members should review the DCI, the ISA report, and other sources to create the final set of strengths, challenges/concerns about performance related to the elements, and strategies to address identified concerns.
The self-study summary report should be evidence-based and if written by a subset of the task force, the full task force should review it and must affirm that they agree with its conclusions.
SOM Accreditation Webpage
  https://www.sc.edu/study/colleges_schools/medicine/internal/lcme_accreditation/index.php

## Slide 5: Self-study Committees
There will be five self-study committees reporting to the Self-study Task Force whose main responsibility with be the completion and analysis of specific sections of the DCI.
The Self-study Committees are:
  Governance, Administration and Resources (Standards 1, 2 and 5)
    Co-chairs: Mr. D. Payne and Dr. C. Taylor
  Academic and Learning Environments (Standard 3)
    Co-chairs: Dr. C. Carter and Dr. M. Orr
  Medical Education Program/Curriculum (Standards 6, 7, 8 and 9)
    Co-chairs: Dr. A. Gandy and Dr. C. Nichols
  Faculty (Standard 4)
    Co-chairs: Dr. W. Carver and Dr. S. Weissman
  Medical Student Experience (Standards 10, 11 and 12)
    Co-chairs: Dr. Dr. Ray and Dr. E. Williams

## Slide 6: Independent Student Analysis
An additional committee comprised of 20 medical students will be charged with developing (LCME provides a template) and administering a school wide survey, compiling the data, and submitting their own independent analysis of their findings.
Co-chairs: Mr. Brice Smoker, M-IV and Ms. Kendall Stalls, M-II

## Slide 7: Timeline for Self-study
August 2023
  Appoint members of the Self-study Task Force, self-study committees, and student independent analysis committee. (Self-study Steering Committee)
  Consider Faculty and Student Town Halls to kick off and explain the self-study process
September 2023
  Task Force meets to review self-study process. Self-study committees begin meeting.
  Student self-study committee meets to review charge and begin work on student survey.
January 2024
  Student survey distributed to student body along with second student town hall to explain the importance of the survey and answer questions/define terms.
  Task Force meets to receive updates from co-chairs on self-study committees progress.

## Slide 8: Timeline for Self-study 2
March 2024
  Student survey data compiled and send to FAL/self-study committees
  Student self-study committee begins their analysis of the data
  Self-study committee review/analyze the ISA data and incorporate it into the relevant sections of the DCI
May 2024
  Student self-study committee completes and submits their final ISA report to FAL and Self-study Task Force for review
  Self-study committees submit their completed DCI to the Self-study Task Force

## Slide 9: Timeline for Self-study 3
June 2024
  Self-study Task Force review and analyze data submitted from the DCI and ISA. Begin preparation of self-study summary report. Develop plans and implement changes to correct issues identified in the self-study process
September 2024
  FAL and Dean update DCI (2024 Graduation Questionnaire), DCI appendices, and self-study summary report with current information.
  Global review of survey package for consistency and accuracy
November 2024
  Survey package (DCI, ISA, Self-study Summary) submitted to LCME

## Slide 10: Timeline for Self-study 4
January 2025
  Prep faculty, students and residents for site visit. Hold mock site visit.
February 2-5, 2025
  Site visit starts with a Sunday evening meeting with the Dean and concludes with a midday meeting with the Dean on Wednesday.